## project progress
Project description
Goal | Predicting CSGO pro match wins
Problem | Seeing contributions to team wins/losses
date | progress | notes/struggles | milestones | other
2021-03-11 | planned workflow, created structure for project, took the day off
2021-03-12 | collecting data | no api for website, learning beautiful soup. Working with html for the first time; using in browser element inspector
|  | requests for websites blocked - have to use user-agent in requests line |  | https://puu.sh/HoAeq/53502e423b.png
2021-03-13 | finished writing code to collect data - starting to write standard cleaning code | (havent run collecting code yet)
2021-03-14 | ran collecting code | lots of troubleshooting for collecting code, rate limited | finished collecting, have csvs
began exploratory analysis
began feature engineering
2021-03-15 | continuing feature engineering |  | finished feature engineering
2021-03-16 | debug and ran data cleaning, feature engineering code |  | have final df, finished data exploration
2021-03-17 | started modelling notebook | finished writing base code, debugged
tested out logreg, svc, knn, rf
2021-03-18 |  | continued feature engineering, pca vs no pca, tested on models above
2021-03-19 | running various xgboost methods on the different feature methods above, pca vs no pca | rs/gs taking way too long on machine, not sure why; had to swap to google colab; colab crashed during night
| trying adaboost | adaboost not as good as rf or xgboost, xgboost sometimes performs a little bit better than rf but mostly rf better
| stretch: started coding a neural network while waiting for gs to finish running on colab | colab keeps crashing, rerunning on deepnote
|  | deepnote no gpu, too slow even for first tasks of gs; reran gs with smaller set (720 fits (5.7k before)) on colab -- probably best to just use rs from now on | models so far: 83% rf, 83% xgboost; f1 is balanced for both
2021-03-20 | getting predictions | working on shap, shap incompatible with latest version of tf
|  | neural network was super fast to run - 13minutes for 200 epochs | finished running neural network, achieved 95% train, 97% val accuracy
2021-03-21 | cleaning up code | creating pipeline for deployment | finished final notebook
2021-03-22 | started on presentation
2021-03-23
2021-03-24
2021-03-25 |  |  | presentation

## models
base models - 50% chosen features (training score) | [5 empty] | comments |  | xgboost
| no pca | pca = 0 | pca n = 1 | pca n = 3 |  | all done with cross-val-score, cv = 10 |  | reg squaredlogerror | reg log | binary logistic (lr = 0.3) | binary logistic (lr = 0.3, a = 5, n = 200)
log | 0.7776 | 0.74958 | 0.5 | 0.74711 |  |  | training | 0.7589 | 0.77132 | 0.81099 | 0.82544
svc | 0.77229 | 0.74596 | 0.5 | 0.73893 |  |  | testing | Accuracy: 0.761442 precision recall f1-score support 0 0.71 0.79 0.75 2527 1 0.82 0.74 0.77 3132 accuracy 0.76 5659 macro avg 0.76 0.76 0.76 5659 weighted avg 0.77 0.76 0.76 5659 | Accuracy: 0.767273 precision recall f1-score support 0 0.76 0.71 0.73 2527 1 0.77 0.82 0.80 3132 accuracy 0.77 5659 macro avg 0.77 0.76 0.76 5659 weighted avg 0.77 0.77 0.77 5659 |  | Accuracy: 0.833539 precision recall f1-score support 0 0.83 0.80 0.81 2527 1 0.84 0.86 0.85 3132 accuracy 0.83 5659 macro avg 0.83 0.83 0.83 5659 weighted avg 0.83 0.83 0.83 5659
knn | 0.75426 | 0.72153 | 0.67 | 0.71804
rf | 0.80017 | 0.73708 | 0.5 | 0.7339 |  |  |  | good balance but not good enough | still not good enough | getting better | best model so far
grid search results: AUC = 0.89
base models - 100% features (training score) | [7 empty] | run time per xgboost model is about 4-5mins on pc, 6-7 mins on colab/deepnote
| no pca (scaler) | no pca, no scaler | pca n = 6 | pca n = 7 |  | bad scores, included # rounds team/opposing team won |  | adaboost
log | 1 |  | 1 | 1 |  |  |  | 0.75708
svc | 1 |  | 1 | 1 |  |  |  | Accuracy: 0.758247 precision recall f1-score support 0 0.75 0.69 0.72 3780 1 0.77 0.81 0.79 4708 accuracy 0.76 8488 macro avg 0.76 0.75 0.75 8488 weighted avg 0.76 0.76 0.76 8488
knn | 0.98476 |  | 0.97579 | 0.97579
rf | 0.99761 |  | 0.9973 | 0.99704
base models - n% features (training score)
| no pca (scaler) | no pca, no scaler | no pca, scaled, with lagged perf
log | 0.8106 | 0.79173 | 0.81386
svc | 0.80118 | 0.78868 | 0.803
knn | 0.80238 | 0.8443 | 0.80158
rf | 0.8208 | 0.8216 | 0.81974
[5 empty] | rf no pca no scaler | precision recall f1-score support 0 0.80 0.78 0.79 2527 1 0.83 0.84 0.84 3132 accuracy 0.82 5659 macro avg 0.82 0.81 0.81 5659 weighted avg 0.82 0.82 0.82 5659
[5 empty] | rf no pca scaler | precision recall f1-score support 0 0.81 0.80 0.81 2493 1 0.84 0.86 0.85 3166 accuracy 0.83 5659 macro avg 0.83 0.83 0.83 5659 weighted avg 0.83 0.83 0.83 5659
neural network
dense 64 relu, dropout 0.5, dense 32 relu, dropout 32 | Epoch 50/50 885/885 [==============================] - 5s 5ms/step - loss: 0.2502 - accuracy: 0.8892 - val_loss: 0.1807 - val_accuracy: 0.9325 | very fast
dense 64 relu drop out 0.3, dense 32 relu dropout 0.3, epoch 200 | Epoch 199/200 885/885 [==============================] - 5s 5ms/step - loss: 0.1393 - accuracy: 0.9457 - val_loss: 0.0693 - val_accuracy: 0.9793 | 13 mins for 200 epochs

## job applications
Date | company | job
2015-03-21 | CryptoEconLab | Data Scientist
| Zachry Integrity Engineering | Machine Learning Developer
| SkiptheDishes | Data Scientist
| Neo Financial | Data, Insights and Analytics Statistician